## Master_Schedule
Overview: This document express the master schedule of project trang_tuyen_dung
| Task |  |  | Start Date | Finish Date | PIC | Note
1. Training
|  | 1.1. Training PHP basic |  |  |  | All team | Seft study
|  | 1.2. Training MySQL basic |  |  |  | All team | Seft study
|  | 1.3. Training JavaScript basic |  |  |  | All team | Seft study
|  | 1.4. Training JSON basic |  |  |  | All team | Seft study
|  | 1.5. Training Smarty engine basic |  |  |  | All team | Seft study
2. Study Jobber Base
|  | 2.1. Study Jobber Base Database |  | 2012-12-03 | 16/03/2012 | VuND
2.2. Study Jobber Base Logic
|  |  | 2.2.1. Create Jobber Base component diagram | 2012-12-03 | 16/03/2012 | TungNS, HoaHM
2.2.2. Create Jobber Base master sequence
2.2.3. Study Logic module of Jobber Base
2.2.4. Study GUI module of Jobber Base
3. Design phase
3.1. Create trang_tuyen_dung component diagram
3.2. Create trang_tuyen_dung master sequence diagram
3.3. Create high level sequence diagram
3.4. Design prototype and update design document
4. Coding phase
4.1. Coding GUI module
4.2. Coding Database module
4.3. Coding Logic module
4.4. Unit test and fix bugs
5. Test phase
5.1. Integration Test and Fix bugs
5.2. Peromance Test and Fix bugs
6. SEO phase
6.1. Develop the SEO items
6.2. Fix bugs SEO item